## Sheet1
Product Backlog
Story ID | Story Name | Status | Complexity points (1 - 5, 5 being the hardest) | Dependencies | Expected Sprints
1 | Come up with three rules | Done | 2 |  | 2016-04-01
2 | Decide what language to use | Done | 3
3 | Design and create the die | Done | 4 | 2
4 | Create user interface | Done | 5 | 2 | 2016-04-08
5 | Create the scoring system | Planned | 5 | 2,3,4
6 | Create first player | Done | 5 | 2,4
7 | Create second player | Done | 5 | 2,4
8 | Player Shooting mechanics | Ongoing | 4 | 2,3,4,6,7 | 2016-04-15
9 | Creating a health system | Planned | 3 | 2,3,4,5,6,7
10 | Create an animation for the die when rolling | 2 | 2 | 2,3,4
11 | Displaying the outcome of the die | Done | 1 | 2,3,4
12 | Calculating the damage to be done | Planned | 3 | 2,3,4,5,6,7,11 | 2016-04-22
13 | Updating the player's health bar | Planned | 2 | 2,3,4,5,6,7,11
14 | Deciding which of the two players gets to play first | Planned | 2 | 1,2,3,4,6,7
15 | Showing the winner | Planned | 2 | 1 to 14